## 0131 3month
Task Name | Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Duration (Weeks) | Task Type | Dependencies
Data Ingest - Setup | Phase 1: Data Foundation | X | [11 empty] | 1 | Core Task
Data Ingest - Sources | Phase 1: Data Foundation |  | X | [10 empty] | 1 | Core Task | Data Ingest - Setup
Data Ingest - Pipeline | Phase 1: Data Foundation |  |  | X | [9 empty] | 1 | Core Task | Data Ingest - Sources
Data Ingest - Testing | Phase 1: Data Foundation |  |  |  | X | [8 empty] | 1 | Core Task | Data Ingest - Pipeline
Transformation - Iteration 1 | Phase 2: Processing & Architecture |  |  |  | X | [8 empty] | 1 | Iterative Task | Data Ingest - Testing
Medallion Architecture - Iteration 1 | Phase 2: Processing & Architecture |  |  |  | X | [8 empty] | 1 | Iterative Task | Data Ingest - Testing
Transformation - Iteration 2 | Phase 2: Processing & Architecture |  |  |  |  | X | [7 empty] | 1 | Iterative Task | Transformation - Iteration 1
Medallion Architecture - Iteration 2 | Phase 2: Processing & Architecture |  |  |  |  | X | [7 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 1
Transformation - Iteration 3 | Phase 2: Processing & Architecture | [5 empty] | X | [6 empty] | 1 | Iterative Task | Transformation - Iteration 2
Medallion Architecture - Iteration 3 | Phase 2: Processing & Architecture | [5 empty] | X | [6 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 2
Analytics - Iteration 1 | Phase 3: Analytics & Insights | [6 empty] | X | [5 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 3
Conversational Analytics - Iteration 1 | Phase 3: Analytics & Insights | [6 empty] | X | [5 empty] | 0.4 | Iterative Task | Analytics - Iteration 1
Analytics - Iteration 2 | Phase 3: Analytics & Insights | [7 empty] | X |  |  |  |  | 1 | Iterative Task | Analytics - Iteration 1
Conversational Analytics - Iteration 2 | Phase 3: Analytics & Insights | [7 empty] | X |  |  |  |  | 0.4 | Iterative Task | Conversational Analytics - Iteration 1
Analytics - Iteration 3 | Phase 3: Analytics & Insights | [8 empty] | X |  |  |  | 1 | Iterative Task | Analytics - Iteration 2
Conversational Analytics - Iteration 3 | Phase 3: Analytics & Insights | [8 empty] | X |  |  |  | 0.4 | Iterative Task | Conversational Analytics - Iteration 2
Analytics - Final Iteration | Phase 4: Optimization & Refinement | [9 empty] | X |  |  | 1 | Iterative Task | Analytics - Iteration 3
Conversational Analytics - Final Iteration | Phase 4: Optimization & Refinement | [9 empty] | X |  |  | 0.4 | Iterative Task | Conversational Analytics - Iteration 3
Data Ready Milestone | Milestones |  |  |  |  | X | [7 empty] | 0.2 | Milestone | Transformation - Iteration 1
Architecture Complete Milestone | Milestones | [6 empty] | X | [5 empty] | 0.2 | Milestone | Medallion Architecture - Iteration 3
Analytics Deployed Milestone | Milestones | [10 empty] | X |  | 0.2 | Milestone | Analytics - Final Iteration
Project Complete Milestone | Milestones | [11 empty] | X | 0.2 | Milestone | Conversational Analytics - Final Iteration