## 0131 6-Month
Task Name | Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Duration (Weeks) | Task Type | Dependencies | Column1 | _1
Data Ingest - Planning & Setup | Phase 1: Data Foundation | X | X | [23 empty] | 2 | Core Task
Data Ingest - Source Identification | Phase 1: Data Foundation |  |  | X | X | [22 empty] | 2 | Core Task | Data Ingest - Planning & Setup
Data Ingest - Pipeline Development | Phase 1: Data Foundation |  |  |  |  | X | X | [20 empty] | 2 | Core Task | Data Ingest - Source Identification
Data Ingest - Testing & Validation | Phase 1: Data Foundation | [6 empty] | X | X | [18 empty] | 2 | Core Task | Data Ingest - Pipeline Development
Transformation - Iteration 1 | Phase 2: Processing & Architecture | [8 empty] | X | [17 empty] | 1 | Iterative Task | Data Ingest - Testing & Validation
Medallion Architecture - Iteration 1 | Phase 2: Processing & Architecture | [8 empty] | X | [17 empty] | 1 | Iterative Task | Data Ingest - Testing & Validation
Transformation - Iteration 2 | Phase 2: Processing & Architecture | [9 empty] | X | [16 empty] | 1 | Iterative Task | Transformation - Iteration 1
Medallion Architecture - Iteration 2 | Phase 2: Processing & Architecture | [9 empty] | X | [16 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 1
Transformation - Iteration 3 | Phase 2: Processing & Architecture | [10 empty] | X | [15 empty] | 1 | Iterative Task | Transformation - Iteration 2
Medallion Architecture - Iteration 3 | Phase 2: Processing & Architecture | [10 empty] | X | [15 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 2
Transformation - Iteration 4 | Phase 2: Processing & Architecture | [11 empty] | X | [14 empty] | 1 | Iterative Task | Transformation - Iteration 3
Medallion Architecture - Iteration 4 | Phase 2: Processing & Architecture | [11 empty] | X | [14 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 3
Transformation - Iteration 5 | Phase 2: Processing & Architecture | [12 empty] | X | [13 empty] | 1 | Iterative Task | Transformation - Iteration 4
Medallion Architecture - Iteration 5 | Phase 2: Processing & Architecture | [12 empty] | X | [13 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 4
Analytics - Iteration 1 | Phase 3: Analytics & Insights | [13 empty] | X | [12 empty] | 1 | Iterative Task | Medallion Architecture - Iteration 5
Conversational Analytics - Iteration 1 | Phase 3: Analytics & Insights | [13 empty] | X | [12 empty] | 0.4 | Iterative Task | Analytics - Iteration 1
Analytics - Iteration 2 | Phase 3: Analytics & Insights | [14 empty] | X | [11 empty] | 1 | Iterative Task | Analytics - Iteration 1
Conversational Analytics - Iteration 2 | Phase 3: Analytics & Insights | [14 empty] | X | [11 empty] | 0.4 | Iterative Task | Conversational Analytics - Iteration 1
Analytics - Iteration 3 | Phase 3: Analytics & Insights | [15 empty] | X | [10 empty] | 1 | Iterative Task | Analytics - Iteration 2
Conversational Analytics - Iteration 3 | Phase 3: Analytics & Insights | [15 empty] | X | [10 empty] | 0.4 | Iterative Task | Conversational Analytics - Iteration 2
Analytics - Iteration 4 | Phase 3: Analytics & Insights | [16 empty] | X | [9 empty] | 1 | Iterative Task | Analytics - Iteration 3
Conversational Analytics - Iteration 4 | Phase 3: Analytics & Insights | [16 empty] | X | [9 empty] | 0.4 | Iterative Task | Conversational Analytics - Iteration 3
Analytics - Iteration 5 | Phase 3: Analytics & Insights | [17 empty] | X | [8 empty] | 1 | Iterative Task | Analytics - Iteration 4
Conversational Analytics - Iteration 5 | Phase 3: Analytics & Insights | [17 empty] | X | [8 empty] | 0.4 | Iterative Task | Conversational Analytics - Iteration 4
Analytics - Iteration 6 | Phase 3: Analytics & Insights | [18 empty] | X | [7 empty] | 1 | Iterative Task | Analytics - Iteration 5
Conversational Analytics - Iteration 6 | Phase 3: Analytics & Insights | [18 empty] | X | [7 empty] | 0.4 | Iterative Task | Conversational Analytics - Iteration 5
Performance Optimization | Phase 4: Optimization & Production | [19 empty] | X | [6 empty] | 1 | Core Task | Analytics - Iteration 6
Production Deployment | Phase 4: Optimization & Production | [20 empty] | X | [5 empty] | 1 | Core Task | Performance Optimization
User Training & Documentation | Phase 4: Optimization & Production | [21 empty] | X |  |  |  |  | 1 | Core Task | Production Deployment
System Monitoring Setup | Phase 4: Optimization & Production | [22 empty] | X |  |  |  | 1 | Core Task | User Training & Documentation
Final Testing & Validation | Phase 4: Optimization & Production | [23 empty] | X |  |  | 1 | Core Task | System Monitoring Setup
Project Handover & Closure | Phase 4: Optimization & Production | [24 empty] | X |  | 1 | Core Task | Final Testing & Validation
Data Foundation Complete Milestone | Milestones | [8 empty] | X | [17 empty] | 0.2 | Milestone | Data Ingest - Testing & Validation
Processing Architecture Complete Milestone | Milestones | [12 empty] | X | [13 empty] | 0.2 | Milestone | Medallion Architecture - Iteration 5
Analytics Platform Ready Milestone | Milestones | [18 empty] | X | [7 empty] | 0.2 | Milestone | Analytics - Iteration 6
Production Deployment Complete Milestone | Milestones | [20 empty] | X | [5 empty] | 0.2 | Milestone | Production Deployment
Project Complete Milestone | Milestones | [23 empty] | X |  |  | 0.2 | Milestone | Project Handover & Closure